## SCHEDULE
RECOMMENDATIONS FOR CHAPTER FACILITIES DURING
HOST INSTITUTION RESPONSES TO COVID-19
IMMEDIATE ACTIONS |  | Date Completed
PLANNING | Description | Date
Lease Agreement Review | Review the house corporation's contractual obligations to the residents and members as well as to the host institution or landlord (if facility is leased).
Personal Property | Develop a plan to secure personal property remaining on the premises.
Security | Review with residents and members the expectations related to chapter facility access. This may include personal access to the chapter facility, storage of personal items, and pre-determined date and time to retrieve personal items.
Cleaning | Arrange for a deep cleaning which should include: chapter facility sanitization; emptying and cleaning of all kitchen equipment including refrigerators and freezers; carpet, flooring, and bathroom cleaning; and removing all refuse.
Property Inspection | Arrange for a daily inspection of the property. Ask a responsible alumnus/alumna or hire a property management company.
Room Checks | Perform room checks and process security deposit returns if needed per lease agreements.
Fine Arts / Historical Items | Fine arts or historical items of significant value should be properly stored and secured to avoid vandalism and potential theft.
Renovation Plans | Consider what, if any, larger projects need to be completed during the summer break while the facility is empty.
COMMUNICATION | Description | Date
Local Authorities | Notify local authorities if the facility will be unoccupied. Provide house corporation contact information in case of emergency. Ask campus and local police to increase patrols in your area to deter burglars and vandals.
Utility Companies | Contact utility companies to ensure proper contact information is on file. Address any special needs.
Mail and Delivery Service | Suspend mail and delivery service to the building.
Host Institution | Share house corporation summer contact information with your host institution.
Neighboring House Corporations | Provide neighboring house corporation contacts with your contact information. Work together to keep an eye each others' facilities or share the cost of hiring a property management company for the period of unoccupancy.
Alarm Monitoring Companies | Update contact information with alarm monitoring companies and keep alarm service active during break.
WEATHER | Description | Date
HVAC Settings | Set air conditioning to 85 to prevent mold and mildew.
Secure Outdoor Items | Prepare for high wind, rain and strong storms. Ensure exterior items are locked, closed up and/or stored inside.
Disaster Planning | Plan for natural disasters, if in an applicable area. Visit www.nhc.noaa.gov for more information.
Gutters & Downspouts | Clean and inspect gutters and downspouts to ensure proper water drainage away from the building during heavy rain.
FIRE SPRINKLERS & ALARMS | Description | Date
Test Detection Systems | Test all fire alarm and detection systems before locking up.
Keep Detection Systems Active | Keep all detection and fire prevention systems active during the break.
Investigate Additional Protective Safeguards | Explore services such as PipeBurst Pro to prevent water damage. Install exterior security cameras with a monitoring service to deter vandalism and assist in notification of any issues while the facility is closed.
DURING EXTENDED BREAK |  | Date Completed
MAINTENANCE | Description | Date
Wiring, Electrical Cords, and Plugs | Check for wear or damage. Replace if necessary. All non-essential items should be unplugged and non-operational.
Roof | Hire a professional to complete an inspection of the roof and address concerns.
Water Heater | Flush out hot water to remove accumulated sediment.
Outdoor Irrigation | Inspect and repair outdoor sprinkler and irrigation systems. Store hoses, secure outdoor water spigots / hose bibs with locks.
Interior Water Supply | Turn off interior water supply ONLY if it will not affect the sprinkler system (if present).
Windows | Caulk and seal windows to prevent water seepage.
Sump Pump | Ensure sump pumps are operating properly.
Kitchen | Thoroughly clean kitchen, kitchen appliances (including refrigerators and freezers) and kitchen fire suppression system.
Cleaning | Perform a deep cleaning and sanitation inside and out, ensuring removal of all refuse.
SCHEDULE INSPECTIONS | Description | Date
Emergency Lighting and Exit Signs | Ensure all systems are in good working order and any necessary repairs are made prior to reopening in the Fall.
Fire / Smoke Detection Systems | Contact a licensed contractor to perform annual maintenance and testing.
Fire Extinguishers | Contact a licensed contractor to perform annual maintenance.
Automatic Sprinkler System | Contact a licensed contractor to perform annual maintenance and testing.
Kitchen Exhaust / Fire Suppression System | Contact a licensed contractor to perform annual maintenance and testing.
HVAC System | Contact a licensed contractor to perform annual maintenance.
SECURITY | Description | Date
Locks & Windows | Check and secure locks, ensure dead bolts are in place. All windows should be firmly closed and locked.
Exterior Lighting | Ensure all exterior lighting is operable.
Exterior Maintenance & Landscaping | Keep exterior maintained to discourage vandalism and demonstrate people are checking on the property or occupying it.
We encourage you to visit our website and print out a copy of our complete
Fraternity / Sorority Risk Management Survey
and conduct a complete walk-through on your own.